Feasibility Analysis

Hostel Management System

CSE347 — Information System Analysis & Design

EXECUTIVE SUMMARY & INTRODUCTION

The Hostel Management System is a web-based application designed to automate and digitize the day-to-day operations of student hostels. This feasibility study evaluates the viability of the system, which has been developed using Python 3, Flask, and MySQL/MariaDB, replacing manual, paper-based record keeping with a centralized digital platform.

The system supports three user roles:

A) Manager (Hostel Manager)

Secure login with authentication (scrypt password hashing)

Student registration and deletion

Hostel, room and room-allocation management (gender-separated)

Attendance management with geo-fenced GPS check-in and analytics

Invoice generation and payment tracking (multiple bills at once, print statements)

Complaint, violation, parcel and visitor management

Mess-off request handling and weekly mess menu updates

Notification system (alerts + free-text notices)

Profile and login detail updates

B) Staff (Caretaker / Cook / Guard)

Secure login with authentication

Register student visitors at the front desk

Receive parcels and notify students

Record student returns

Mark own geo-fenced attendance with personal stats and charts

C) Student (Resident Entity)

Secure login with authentication

View personal profile and hostel/room details

Mark geo-fenced attendance with personal stats and trend charts

View weekly mess menu

Register complaints and feedback

Log check-in/check-out with reason

Apply for mess-off

Receive parcel notifications and self-collect parcels

View invoices and print statements

The Manager role encompasses all hostel management responsibilities, ensuring streamlined oversight and centralized control. In addition, the system is deployed as a live free web copy (Render web service + Aiven free MySQL over TLS) and supports on-demand data synchronization between the local and web databases.

1. LEGAL & ETHICAL FEASIBILITY

Licensing Compliance: The system is built entirely on open-source components — Flask (BSD-3-Clause), Python (PSF), Leaflet (BSD-2-Clause), Chart.js (MIT), and MySQL/MariaDB (GPL) — removing any risk of legal copyright or software non-compliance.

Data Privacy Ethics: Personal resident identifiers (NID/Passport strings, contact data) are kept in normalized, secured tables; only the respective student and authorized management can view sensitive disciplinary and payment history.

Academic Integrity: This project is the team's own work, developed for the CSE347 course; all referenced materials are open source and properly attributed.

2. TECHNICAL FEASIBILITY

2.1 Hardware Requirements

Server: Any system running Python 3 + MySQL/MariaDB stack

Minimum RAM: 2 GB (4 GB recommended)

Processor: Intel Core i3 or equivalent

Storage: 100 MB free space (excluding OS)

Network: Standard LAN/Wi-Fi for multi-user access

Mobile GPS: A smartphone or device with GPS for geo-fenced attendance check-in

2.2 Software Requirements

Operating System: Windows, Linux, or macOS

Runtime: Python 3.10+ (tested on 3.14)

Web Framework: Flask 3.x with Jinja2 server-rendered templates

Database: MySQL 8.0+ / MariaDB 10.4+

Database Driver: mysql-connector-python

Frontend: Any modern browser (Chrome, Firefox, Edge); HTML + CSS + a small vanilla-JS file

Libraries: Chart.js (charts), Leaflet + OpenStreetMap (maps), gunicorn (web server for deployment)

Development Tools: XAMPP (local MySQL), VS Code, Git

2.3 Technology Assessment

Python + Flask: Mature, well-documented server-side stack with a large ecosystem. Server-rendered Jinja2 templates keep the app fast and simple, and the same codebase runs locally and on the web.

MySQL/MariaDB: Robust relational database with triggers, foreign key constraints, and referential integrity. The schema (18 tables + 3 triggers) is normalized and derived directly from the UML class diagram.

Leaflet/OpenStreetMap: Free geo-fencing without paid API keys — students/staff can only mark attendance inside the hostel's GPS radius.

Chart.js: Free, responsive analytics charts (attendance donut + 14-day trend).

Deployment: Render (free web service) + Aiven free MySQL over TLS — zero hosting cost.

2.4 Security Assessment (Implemented)

Passwords are hashed with scrypt (Python's standard library) — never stored in plaintext.

Session-based authentication with role-guarded routes (Manager / Staff / Student).

All database operations use parameterized queries (%s placeholders) — SQL-injection safe.

Strict SQL mode rejects invalid data at the database level.

Database socket timeouts (15 s) prevent a dead connection from hanging a request.

Geo-fencing uses browser geolocation over HTTPS on deployed servers (localhost always works).

3. SCHEDULE FEASIBILITY

3.1 Estimated Timeline (PERT Analysis)

The schedule was estimated using the PERT three-point technique (Optimistic to, Most Likely tm, Pessimistic tp), with the expected duration te = (to + 4tm + tp) / 6 and variance σ² = ((tp − to) / 6)².

| Task description | Task ID | Dependency | Opt. (to) | ML (tm) | Pess. (tp) | te (days) | Variance σ² |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning & Scope Definition | T1 | None | 2 | 3 | 4 | 3 | 0.11 |
| Requirements Gathering | T2 | T1 | 3 | 5 | 7 | 5 | 0.44 |
| Software Requirement Specification (SRS) | T3 | T2 | 2 | 4 | 6 | 4 | 0.44 |
| Database Design & Implementation | T4 | T3 | 3 | 4 | 5 | 4 | 0.11 |
| Development Environment Setup (Python, Flask, MySQL, XAMPP) | T5 | T3 | 1 | 2 | 3 | 2 | 0.11 |
| UI/UX Design Prototype | T6 | T3 | 6 | 8 | 10 | 8 | 0.44 |
| Authentication & Authorization Module | T7 | T4, T5, T6 | 5 | 7 | 9 | 7 | 0.44 |
| Manager Dashboard Module | T8 | T6, T7 | 5 | 7 | 10 | 7.17 | 0.69 |
| Student Management Module | T9 | T7 | 5 | 7 | 9 | 7 | 0.44 |
| Attendance & Geo-fencing Module | T10 | T9 | 4 | 5 | 7 | 5.17 | 0.25 |
| Invoice & Payment Module | T11 | T10 | 4 | 6 | 8 | 6 | 0.44 |
| Mess-Off & Menu Management Module | T12 | T9 | 3 | 4 | 5 | 4 | 0.11 |
| Visitor & Parcel Management Module | T13 | T8, T9 | 3 | 4 | 6 | 4.17 | 0.25 |
| Complaint & Feedback Module | T14 | T8, T9 | 3 | 4 | 5 | 4 | 0.11 |
| Frontend Integration & Design | T15 | T6, T8, T9 | 4 | 5 | 7 | 5.17 | 0.25 |
| Testing, Security Validation & Bug Fixing | T16 | T11–T15 | 7 | 10 | 13 | 10 | 1 |
| Deployment, Documentation & User Training | T17 | T16 | 3 | 5 | 7 | 5 | 0.44 |

3.2 PERT Calculation Summary

Expected project length (critical path): T1 + T2 + T3 + T4 + T6 + T7 + T9 + T10 + T11 + T16 + T17 = 3 + 5 + 4 + 4 + 8 + 7 + 7 + 5.17 + 6 + 10 + 5 = 64.17 days

Project critical path: 1 → 2 → 3 → 4 → 7 → 5 → 8 → 10 → 11 → 13 → 16 → 17

Project length variance, σ² = 0.11 + 0.44 + 0.44 + 0.11 + 0.44 + 0.44 + 0.44 + 0.25 + 0.44 + 1 + 0.44 = 4.55

Project length standard deviation, σ = 2.13 days

With σ = 2.13, there is a high probability the project finishes within approximately 64 ± 4 days — roughly 2 to 2.5 months.

3.3 Deployment (Already Completed)

Development is complete and the system is already deployed. The live web copy runs on Render with an Aiven MySQL database over TLS, and a GET /healthz endpoint reports status for uptime monitors. Deployment to the free hosting took approximately 2 days (one-time database import + web service setup + environment variables).

4. ECONOMIC FEASIBILITY

4.1 Development Costs

| Cost Item | Amount (৳) |
| --- | --- |
| Software stack (Python, Flask, MySQL, Chart.js, Leaflet, VS Code) | 0 (open source) |
| System analysis & design (6 weeks) | 5,000 |
| Programming & module development (~8 weeks) | 15,000 |
| UI/UX design | 3,000 |
| Testing, bug fixing & documentation | 2,000 |
| Total Development Cost | 25,000 |

4.2 Hardware Costs

| Cost Item | Amount (৳) |
| --- | --- |
| Development laptop — 20% project allocation of a ৳60,000 device | 12,000 |
| Web server (Render free tier — no dedicated hardware) | 0 |
| Total Hardware Cost | 12,000 |

4.3 Operational Costs

| Cost Item | Amount (৳) |
| --- | --- |
| Domain name (.com) | 800 / year |
| SSL/HTTPS (Let's Encrypt — free) | 0 |
| Electricity & internet share | 1,000 / month (12,000 / year) |
| Part-time maintenance labor | 2,000 / month (24,000 / year) |
| Database backup storage | Negligible |
| Total Operational Cost | 36,800 / year |

4.4 Hosting Services — if free tiers are exhausted

The project currently runs entirely on free tiers (Render web service + Aiven free MySQL + UptimeRobot). If the free tiers expire, keeping the site live would cost approximately:

| Service | Free tier (included) | Paid upgrade cost | Per year (৳) |
| --- | --- | --- | --- |
| Render web service | ৳0 (sleeps when idle, 30-day expiry) | ~$7 / month ≈ ৳830 / month | 9,960 |
| Aiven MySQL (cloud database) | ৳0 (powers off when idle) | ~$15 / month ≈ ৳1,780 / month | 21,360 |
| UptimeRobot uptime monitor | ৳0 (basic monitors) | ~$5 / month ≈ ৳600 / month | 7,200 |
| Total if paid tiers needed | — | — | 38,520 / year |

4.5 Cost-Benefit Analysis

BENEFITS:

Elimination of paper records and printing costs

Reduced administrative labor hours

Faster fee collection and tracking (fewer defaults)

Improved record accuracy and accessibility

Real-time data availability for decision making

Reduced complaint resolution time

SAVINGS ESTIMATE (per year):

| Savings item | Estimated value (৳) |
| --- | --- |
| Paper & stationery eliminated | 15,000 – 30,000 |
| Administrative hours saved (100–200 hrs @ ৳200/hr) | 20,000 – 40,000 |
| Improved fee collection (reduced defaults) | Variable, positive |
| Reduced complaint resolution time | Variable, positive |
| Total estimated annual savings | 35,000 – 70,000+ |

SUMMARY: The one-time project cost is ৳37,000 (৳25,000 development + ৳12,000 hardware) with ৳0 recurring cost on the current free hosting tiers. Even if paid hosting becomes necessary (~৳38,520/year), total costs remain below the estimated annual savings of ৳35,000–70,000+. The estimated payback period is approximately 1 to 1.5 years, after which the system generates net savings.

5. OPERATIONAL FEASIBILITY

5.1 User Acceptance

Manager: The system significantly reduces manual paperwork. Attendance, fee management, complaint tracking, and visitor logging become centralized and searchable, with real-time analytics dashboards.

Staff: Front-desk tasks (visitor registration, parcel receiving, student-return logging) become one-click operations with automatic student notifications.

Students: Self-service features (profile, complaint registration, mess-off requests, attendance viewing, parcel self-collection) reduce dependency on administrative staff.

5.2 Operational Changes

Current Process: Paper registers for attendance, fee collection, visitor logs, complaints, and mess management.

Proposed Process: All records stored digitally. Managers, staff and students log in to role-based dashboards; the live web copy is accessible from any phone with GPS, and data can be synchronized between local and web databases on demand.

5.3 Training Requirements

Manager Training: Minimal (2–3 hours). The UI is intuitive with form-based inputs, tabular displays, and chart dashboards.

Staff Training: Minimal (1 hour). Simple front-desk forms.

Student Training: Minimal (1 hour). Familiar web interface similar to standard portals.

5.4 Support & Maintenance

Python/Flask/MySQL knowledge is widely available.

The system runs locally on XAMPP (free) and on the web via Render + Aiven.

Database backups can be performed via phpMyAdmin, mysqldump, or the project's own sync scripts.

No proprietary vendor lock-in — all components are open source.

ARCHITECTURAL RISK ANALYSIS & SECURITY BLUEPRINT

The system design incorporates strict security engineering standards:

1. Cryptographic Safeguards: All authentication passwords are hashed with scrypt before being written to disk. Plaintext storage is strictly prohibited.

2. Prevention of SQL Injection: All data-access operations use parameterized queries (%s placeholders) — no string-concatenated SQL.

3. Role-Based Access Control: Every route is guarded by role decorators, so a student can never reach manager functions and vice versa.

4. Geo-fencing Privacy: Attendance uses the browser's GPS over HTTPS; the hostel's coordinates and radius are enforced server-side.

5. Database Resilience: 15-second socket timeouts and a background-thread backfill ensure a hung or idle database connection can never stall user requests.

6. Server-Side Input Sanitization: All form inputs are validated and stripped server-side before processing.

Conclusion & Recommendation

The Hostel Management System is feasible across all dimensions:

Technical: YES — Built and running on proven, stable technologies (Python 3 + Flask + MySQL).

Operational: YES — Intuitive interface, minimal training required for all three roles.

Economic: YES — One-time cost of ৳37,000, ৳0 recurring on free hosting, savings of ৳35,000–70,000+ per year.

Schedule: YES — Completed within the PERT-estimated ~64-day timeline (critical path), σ = 2.13 days.

Legal/Ethical: YES — Open-source stack, no licensing conflicts.

Recommendations for Implementation

Already implemented:

Scrypt password hashing (secure, industry-standard).

Parameterized queries throughout — SQL-injection safe.

Role-guarded routes and strict SQL mode.

HTTPS/SSL on the deployed site.

Responsive mobile interface.

Future recommendations:

Set up automated daily database backups.

Add a 'Forgot Password' feature for user convenience.

Add pagination for large datasets (attendance, invoices).

Provide a printable PDF attendance report per student.

Overall Verdict: The project is highly feasible and has already been successfully implemented and deployed. With minor future enhancements, it will continue to improve efficiency, transparency, and record accuracy in hostel management operations, serving the three roles of Manager, Staff, and Student.